## Summary
Civic Operations: Team Log Book
NUS ISS, Intelligent Reasoning Systems practice module, Team MANTIS (Group 23) · 5 September to 21 October 2026
Member | Student ID | GitHub account | Commits in the period | Components and main work
Khalid Alhazmi | A0361128J | hazmika | 33 | Urgency, Prioritisation
Mohammad Alharthi | A0354097W | engharthi | 2 | Agency and skill routing, External factors, Crew deployment and routing, GPU experiment run, independent label check
Nabeel Taresh | A0352296X | Nabeel | 13 | Duplicate detection, Fake request detection, Admin questions
Indish Sankalp Sandeep | A0351383E | DevelopingGod, Sankalp Indish | 86 | Intake bot, Emergency check, Credibility and escalation, Predictive alerting, application, integration, testing, documents
Meetings
14 MS Teams meetings of over an hour each, from the project start on 5 September. Recorded durations cover 6.5 hours across the meetings in the tracker. See the Meetings sheet.
Mohammad delivered his three packages as files, so his work shows in the deliveries below rather than in commits. Every entry names its record: the tracker, meeting notes, git history or a delivered package.

## Log
Date | Member | Type | Activity | Output and evidence
2026-09-05 | All | Meeting | MS Teams meeting: First meeting: system components, evaluation points, dataset, GitHub | Meetings sheet (team record)
2026-09-07 | All | Meeting | MS Teams meeting: Second meeting: report on assigned components, input and output template | Meetings sheet (team record)
2026-09-08 | Sankalp | Setup | GitHub repository set up: project structure, meeting logs and templates. The full dataset kept local, a documented slice committed | Repository (git, 8 Sep)
2026-09-09 | All | Meeting | MS Teams meeting: Component design and the initial data flow diagram | Meetings sheet (team record)
2026-09-09 | Nabeel | Design | Design of his two assigned components and the initial data flow diagram, 1.5 hours | Tracker (9 Sep)
2026-09-09 | Sankalp | Proposal | Proposal kickoff deck, and an architecture that commits to all four technique groups | Kickoff deck (git, 9 Sep)
2026-09-11 | All | Meeting | MS Teams meeting: Project proposal content agreed | Meetings sheet (team record)
2026-09-11 | Nabeel | Research | NYC 311 field inventory: complaint families, responsible agencies, the input fields on 311 request pages | GitHub (git, 11 Sep)
2026-09-12 | All | Meeting | MS Teams meeting: Proposal finalised for submission | Meetings sheet (team record)
2026-09-12 | Mohammad | Research | Analysis of the NYC 311 workflow and the mapping from agency to crew skill, 3 hours | Tracker (12 Sep)
2026-09-12 | Sankalp | Proposal | Project proposal and final system architecture written for submission | Proposal (git, 12 Sep), submitted 13 Sep
2026-09-16 | Sankalp | Build | Post proposal build baseline: data pipeline over NYC 311 Open Data, locked component input and output contracts | Data pipeline, processed tables, contracts (git, 18 Sep)
2026-09-18 | Sankalp | Planning | Planning session: build plan, task board of 31 tasks with owners and due dates, decisions log | Tracker: Task Board T01 to T31, Decisions Log (tracker)
2026-09-18 | Sankalp | Research | Daily demand baselines for Predictive alerting, data preparation notebook rerun | Notebook 01 (git, 18 Sep)
2026-09-19 | All | Meeting | MS Teams meeting: Team meeting | Meetings sheet (team record)
2026-09-19 | Sankalp | Documentation | Read Me First guide, a personal reference guide for each member, shared system context for consistent work | 05_Team_Workspace/01_Start_Here and 02_Personal_Guides (git, 19 Sep)
2026-09-23 | All | Meeting | Team meeting: views for admin, management, crew and citizen, how to show the IRS concepts, core components in the presentation | Meeting notes (05_Team_Workspace/08_Meetings, 23 Sep)
2026-09-23 | All | Meeting | MS Teams meeting: Portals and presentation planning | Meetings sheet (team record)
2026-09-25 | All | Meeting | MS Teams meeting: Team meeting | Meetings sheet (team record)
2026-09-25 | Khalid | Build | First Urgency component upload | GitHub upload (git, 25 Sep)
2026-09-26 | All | Meeting | MS Teams meeting: Team meeting | Meetings sheet (team record)
2026-09-26 | Sankalp | Presentation | Animated demo, research gap table and technique, component and metric tree for the presentation | 04_Course_and_Proposal/03_Proposal_Presentation (git, 26 Sep)
2026-09-27 | Sankalp | Presentation | Speaker cue card and examiner question preparation | Cue card, Examiner Q&A (git, 27 Sep)
2026-09-28 | All | Presentation | Proposal presentation to the examiners | Presentation deck, NUS ISS theme (git, 28 Sep)
2026-10-02 | All | Meeting | MS Teams meeting: Team meeting | Meetings sheet (team record)
2026-10-05 | All | Meeting | MS Teams meeting: Team meeting | Meetings sheet (team record)
2026-10-05 | Mohammad | Research | Ran the language model experiment notebook on his GPU machine | Verified GPU run results (git, 5 Oct)
2026-10-05 | Sankalp | Research | Component specification, data findings document, 156 new hand written test lines, second experiment notebook | 05_Team_Workspace/03_Specification_and_Contracts (git, 5 Oct)
2026-10-07 | Sankalp | Build | Intake bot, Emergency check, Credibility and Predictive alerting built against the GPU results, evidence pack and experiment register | 03_Research/evidence (git, 7 Oct)
2026-10-08 | Sankalp | Research | Credibility fairness gate closed, glossary, slot filling measured on hand marked spans, contribution report | Gates in component_status.json (git, 8 Oct)
2026-10-09 | All | Meeting | MS Teams meeting: Team meeting | Meetings sheet (team record)
2026-10-09 | Sankalp | Build | Shipped models committed, repository tidied | 01_Application/models (git, 9 Oct)
2026-10-11 | Khalid | Build | Urgency component: rules, hazard knowledge base, service impact rules, tests | Branch khalid_code (git, 11 to 13 Oct)
2026-10-13 | Sankalp and Khalid | Meeting | MS Teams meeting: Working session | Meetings sheet (team record)
2026-10-15 | Mohammad | Delivery | Agency and skill routing v1.1.0 with its research report and tests | Delivered package, report built 15 Oct
2026-10-15 | Nabeel | Build | Duplicate detection and Fake request detection, tuned on 295 hand checked real pairs | Branch nabeel_c05_c06 (git, 15 Oct)
2026-10-15 | Nabeel | Research | Admin questions v1.1.0 benchmarked on 74 gold questions written before any strategy ran, results and change logs | Branch nabeel_c12 (git, 15 Oct)
2026-10-15 | Sankalp | Build | App backend with every component as a measured plugin, citizen, crew and staff portals | 01_Application/app (git, 15 Oct)
2026-10-16 | Khalid | Delivery | Urgency and Prioritisation final version on his branch | Commit 906b77a, pinned in the app (git, 16 Oct)
2026-10-16 | Sankalp | Review | Reviewed Urgency and Prioritisation on a fresh copy, sent findings to Khalid | Review message (16 to 18 Oct)
2026-10-18 | Mohammad | Delivery | External factors v1.0.0 with OpenStreetMap facilities, 90 tests | Delivered package (18 Oct)
2026-10-18 | Sankalp | Integration | One folder per component, teammates' components merged, Intake address repair, accounts and roles, Docker containers | Pull requests 2 and 3 merged (git, 18 Oct)
2026-10-19 | Mohammad | Delivery | Crew deployment and route optimisation v1.0.0, runtime and full research package | GitHub and delivered package (git, 19 Oct)
2026-10-19 | Mohammad | Review | Independent label check of 30 intake test messages | Returned sheet, 03_Research/experiments (19 Oct)
2026-10-19 | Sankalp | Integration | Crew deployment plugged in, browser tests at three screen sizes, setup guide, numbered layout, AI ranking reasons on every card | Pull requests 4 and 5 merged (git, 19 Oct)
2026-10-20 | All | Meeting | MS Teams meeting: Team meeting | Meetings sheet (team record)
2026-10-20 | Sankalp | Build | Crews get their routes automatically with staff pull back, street maps with the depot and the crew's position, a deadline for every request type, linked duplicates that close with their original, group report rebuilt, setup guide and handbook | Pull requests 12 and 13 (git, 20 Oct)
2026-10-21 | Nabeel | Deployment | Deployed the app on his DigitalOcean server from the public repository, live at http://157.230.191.175/ | Live server, checked 21 Oct

## Meetings
Date | Mode | Topic | Hours (recorded) | Attendees
2026-09-05 | MS Teams | First meeting: system components, evaluation points, dataset, GitHub | 2 | All four members
2026-09-07 | MS Teams | Second meeting: report on assigned components, input and output template | 1.5 | All four members
2026-09-09 | MS Teams | Component design and the initial data flow diagram | 1.5 | All four members
2026-09-11 | MS Teams | Project proposal content agreed | 1.5 | All four members
2026-09-12 | MS Teams | Proposal finalised for submission | over 1 | All four members
2026-09-19 | MS Teams | Team meeting | over 1 | All four members
2026-09-23 | MS Teams | Portals and presentation planning | over 1 | All four members
2026-09-25 | MS Teams | Team meeting | over 1 | All four members
2026-09-26 | MS Teams | Team meeting | over 1 | All four members
2026-10-02 | MS Teams | Team meeting | over 1 | All four members
2026-10-05 | MS Teams | Team meeting | over 1 | All four members
2026-10-09 | MS Teams | Team meeting | over 1 | All four members
2026-10-13 | MS Teams | Working session | over 1 | Sankalp and Khalid
2026-10-20 | MS Teams | Team meeting | over 1 | All four members
14 MS Teams meetings in total over the project, each over one hour.

## By member
Member | Entries in the log | Deliveries | Meetings attended
Khalid Alhazmi | 19 | 16 Oct: Urgency and Prioritisation final version on his branch | 14 MS Teams
Mohammad Alharthi | 21 | 15 Oct: Agency and skill routing v1.1.0 with its research report and tests. 18 Oct: External factors v1.0.0 with OpenStreetMap facilities, 90 tests. 19 Oct: Crew deployment and route optimisation v1.0.0, runtime and full research package | 13 MS Teams
Nabeel Taresh | 20 | Code on GitHub, see Log | 13 MS Teams
Indish Sankalp Sandeep | 34 | Code on GitHub, see Log | 14 MS Teams